## project
Team Too
[14 empty] | Period Highlight: |  |  |  |  | 15
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | [9 empty] | Plan |  |  | Actual
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Project Plan Presentation | 5 | 1 | 5 | 1 | 100%
Requirements Document | 5 | 3 | 6 | 8 | 100%
Back-End development | 6 | 8 | 6 | 14 | 100%
Connecting to FHIR | 6 | 1 | 6 | 3 | 100%
Class layouts | 6 | 1 | 6 | 3 | 100%
Front-End Development | 6 | 8 | 6 | 14 | 100%
Dashboard | 7 | 2 | 7 | 14 | 100%
Software Development | 8 | 4 | 7 | 14 | 100%
Project Progress Report 1 | 8 | 1 | 9 | 1 | 100%
Graphs | 9 | 2 | 8 | 13 | 100%
Reports | 12 | 2 | 10 | 14 | 100%
Connect Front and Back ends | 12 | 2 | 10 | 12 | 100%
Connection to other groups | 11 | 2 | 12 | 12 | 100%
Project Progress Report 2 | 12 | 1 | 7 | 7 | 100%
User Guide | 13 | 2 | 12 | 13 | 100%
Testing | 13 | 3 | 10 | 14 | 100%
Final Project | 15 | 1 | 15 | 15 | 100%